## 24-month Gantt
advanCARE — Year 1 & Year 2 Gantt chart (revised budget)
Proposed 24-month schedule. M1 = project start; dates pending. Revised equipment and SMS scope included.
Colored bars = activity window. ◆ = milestone. Amber section = proposed Months 19–24.
Budget totals need reconciliation; see Budget source.
[5 empty] | YEAR 1 | [11 empty] | YEAR 2
ID | Activity / milestone | Start | End | Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
FOUNDATION & VALIDATION
01 | Mobilize project team and governance | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
02 | LGU / barangay MOUs and cost sharing | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
03 | Baseline survey and household digitization | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
04 | Privacy, clinical protocols and referral partners | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
05 | Procure equipment and connectivity | 1 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
06 | Complete pilot platform and verify real-use readiness | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07 | Recruit, screen and train first caregiver cohort | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08 | GATE: pilot readiness | 2 | 2 | 1 | bar: YEAR 1 2
CORE CARE PILOT
09 | Enroll households and assist first bookings | 2 | 4 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Deliver home care and post-discharge follow-up | 2 | 4 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Activate telehealth equipment in pilot sites | 3 | 4 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Review SLA, repeat use and caregiver continuity | 2 | 4 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | GATE: approve municipal expansion | 4 | 4 | 1 | bar: YEAR 1 4
MUNICIPAL EXPANSION
14 | Expand to 8–12 barangays in pilot municipality | 5 | 9 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Introduce pooled NEMT and referral coordination | 5 | 9 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Add respite packages, family updates and Rx routing | 5 | 9 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Complete tier registry and LGU reconciliation | 3 | 6 | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Add SMS, local languages and assisted access | 5 | 9 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | GATE: confirm municipal results | 9 | 9 | 1 | bar: YEAR 1 9
PROVINCIAL EXPANSION
20 | Stage expansion into additional municipalities | 10 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
21 | Formalize CVMC / institutional care contracts | 10 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
22 | Scale caregiver cohorts and train local trainers | 10 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
23 | Add elder knowledge-transfer wellness sessions | 10 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
24 | Introduce supervised workflow automation | 10 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
25 | Scale cloud hosting and performance monitoring | 13 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
26 | GATE: review provincial expansion | 18 | 18 | 1 | bar: YEAR 2 18
CONSOLIDATION & SUSTAINABILITY
27 | Optimize tier mix and rural cross-subsidy | 19 | 24 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
28 | Renew LGU / institutional agreements | 19 | 24 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
29 | Evaluate endline outcomes and affordability | 22 | 24 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
30 | Prepare continuation plan and final reporting | 23 | 24 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
31 | GATE: approve continuation beyond Year 2 | 24 | 24 | 1 | bar: YEAR 2 24
CONTINUOUS PROJECT SUPPORT
32 | Personnel, supervision and operating support | 1 | 24 | 24 | bar: YEAR 1 1 to YEAR 2 24
33 | Quality, safeguarding and caregiver re-screening | 2 | 24 | 23 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
34 | Quarterly LGU billing and financial review | 3 | 24 | 22 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
ADDED EQUIPMENT & COMMUNICATIONS
35 | Commission PBX phones and support desk | 2 | 3 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Install servers, rack, network and storage | 2 | 3 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | Deploy generators and resilient site connectivity | 2 | 3 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Test backup power, failover and support procedures | 3 | 4 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Operate SMS, connectivity and infrastructure upkeep | 5 | 24 | 20 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Schedule details
Schedule basis and activity details
Schedule status | Proposed planning baseline, prepared 17 October 2026. Dates and owners are not yet approved.
Time basis | Year 1 = M1–M12; Year 2 = M13–M24. All activity windows include both start and end months.
Source timing | Phase 0 weeks 1–6 mapped to M1–M2. Phase 1 M2–M4; Phase 2 M5–M9; Phase 3 M10–M18 follow the vault.
Assumed timing | Within-phase task dates, equipment commissioning and all M19–M24 dates are proposed. The expense workbook specifies years, not monthly timing.
Existing implementation | App, API, staff console and care-loop prototype already exist as of 16 October. M1–M2 covers completion and validation for real use.
Source priority | Current .brain and implementation supersede older handoff snapshots. Research informs scope, not confirmed delivery dates.
Budget interpretation | Annual amounts support workstreams. No monthly cost allocation or grant disbursement schedule is inferred. Blank Year 2 costs remain blank.
Survey scope | Budget funds 16 enumerators/digitizers across four LGUs once in Year 1. Service rollout starts with one LGU; survey geography requires confirmation.
Equipment discrepancy | Budget row 44 says Twenty (25) kits; row 42 says Two (3) printers. Amounts imply 25 kits and 3 printers. Confirm quantities.
Funding gaps | Year 2 has no new enumerator line or explicit domain / office-supply renewal. Confirm internet provision covers Starlink service.
Budget reconciliation | Listed expenses exceed the stated Year 1 total by PHP 38,000; Year 2 detail is PHP 780,000 below the stated total. Figures are preserved.
Dependencies | IDs describe prerequisites or coordination links. Same-month work needs within-month sequencing. Gates require evidence before expansion.
Editing | Edit amber Start/End month cells on the Gantt (1–24). Duration, bars and milestone position update. Dependencies do not auto-reschedule.
Review cadence | Weekly pilot reviews and quarterly quality / finance reviews are continuous work windows, not separate monthly spending commitments.
ID | Activity | Dependencies | Expected output / gate | Source / timing basis | Budget alignment | Gantt row
01 | Mobilize project team and governance | — | Project leader, laborers, staff and monitoring roles assigned | Budget rows 5–17; Implementation Plan §3 | Personnel, both years | 9
02 | LGU / barangay MOUs and cost sharing | 01 | One municipality and 2–3 barangays; signed 50/50 funding mechanism | Implementation Plan §3 Phase 0; ADR-001 | Project staff and consulting | 10
03 | Baseline survey and household digitization | 01,02 (site access) | Baseline access, cost and care gaps; four-LGU survey scope to confirm | Implementation Plan §3 Phase 0; Budget row 13 | Enumerators / digitizers, Year 1 only | 11
04 | Privacy, clinical protocols and referral partners | 01 | Consent review, escalation protocol, RHU/CVMC coordination and hotline | TODO: non-code dependencies; Implementation Plan §3 | Consulting and staff | 12
05 | Procure equipment and connectivity | 01 | Computers, scanner/printers, telehealth kits and Starlink commissioned | Budget rows 39–51 | Equipment under MOOE, Year 1 only | 13
06 | Complete pilot platform and verify real-use readiness | 01,04 | Validate existing care loop; separate demo data, secure storage and owned AI key | TODO P1–P4; ARCHITECTURE §§3–6; actual frontend/backend | Laborers, AI, hosting and internet subscriptions | 14
07 | Recruit, screen and train first caregiver cohort | 01,04 | 15–20 screened caregivers, 40-hour training and skill badges | Implementation Plan Phase 0; Service Catalog §4 | Training, transport and utilities | 15
08 | GATE: pilot readiness | 02,03,04,06,07 | 30–50 households; 15–20 caregivers; signed cost sharing and ready care loop | Implementation Plan Phase 0 exit | Milestone | 16
09 | Enroll households and assist first bookings | 08 | BHW-led multilingual onboarding and published tier / service prices | Implementation Plan Phase 1 and §4 | Staff, transport and utilities | 18
10 | Deliver home care and post-discharge follow-up | 08 | Personal care, basic nursing support and respite; one formal follow-up | Implementation Plan Phase 1 | Staff and operating support | 19
11 | Activate telehealth equipment in pilot sites | 04,05,08 | Test clinician connectivity, operator training and escalation workflow | Budget telehealth / Starlink; Mobile App Specification | Year 1 equipment and training | 20
12 | Review SLA, repeat use and caregiver continuity | 08 | Weekly operations review with family feedback and corrective actions | Implementation Plan Phase 1 | Monitoring staff | 21
13 | GATE: approve municipal expansion | 09,10,11,12 | >60% SLA; >40% repeat use in 60 days; >70% caregiver retention | Implementation Plan Phase 1 exit | Milestone | 22
14 | Expand to 8–12 barangays in pilot municipality | 13 | Denser caregiver coverage and BHW enrollment network | Implementation Plan Phase 2 | Staff, training, transport and utilities | 24
15 | Introduce pooled NEMT and referral coordination | 13,04 | Shared transport routes and BHW / tele-nurse routing process | Implementation Plan Phase 2; Centene research | Transport and staff | 25
16 | Add respite packages, family updates and Rx routing | 13 | Long-distance family support and verified pharmacy / Yakap pathways | Implementation Plan Phase 2; Homage and Auxilio research | Staff, AI and hosting | 26
17 | Complete tier registry and LGU reconciliation | 02,06 | Server-side memberships; subsidy report and quarterly billing evidence | TODO P4; Reporting Specifications Table 4 | Laborers and staff | 27
18 | Add SMS, local languages and assisted access | 13,06 | Test low-bandwidth fallbacks and Tagalog / Ilocano / Ybanag support | TODO Later; Implementation Plan §§4,6 | Laborers, internet and bulk SMS (row 35) | 28
19 | GATE: confirm municipal results | 14,15,16,17,18 | 300–500 active members; lower transport cost; >70% discharge follow-through | Implementation Plan Phase 2 exit | Milestone | 29
20 | Stage expansion into additional municipalities | 19 | New LGU agreements and rollout waves as capacity and demand permit | Implementation Plan Phase 3 | Staff and Year 2 field expenses | 31
21 | Formalize CVMC / institutional care contracts | 19,04 | Badged hospital watchers and institutional revenue to support rural care | Implementation Plan Phase 3; Service Catalog §2 | Staff and consulting | 32
22 | Scale caregiver cohorts and train local trainers | 19,07 | Repeat screening, continuity incentives and trainer pipeline | Implementation Plan §§3,6; Honor research | Training, transport and utilities | 33
23 | Add elder knowledge-transfer wellness sessions | 19 | Intergenerational sessions integrated into wellness visits | Implementation Plan Phase 3 | Staff and field expenses | 34
24 | Introduce supervised workflow automation | 19,06 | Async matching notifications, care summaries and reporting with oversight | Agentic Architecture; ADR-006; TODO Later | Laborers, AI and hosting | 35
25 | Scale cloud hosting and performance monitoring | 20 (rollout demand) | Stage 2 capacity, backup/recovery checks and service monitoring | Budget row 32: Stage 2 Year 2; ARCHITECTURE | Year 2 hosting: PHP 1,500,000 | 36
26 | GATE: review provincial expansion | 20,21,22,23,24 | Review coverage, SLA, caregiver retention and unit economics before growth | Phase 3 ends M18; review gate proposed | Milestone | 37
27 | Optimize tier mix and rural cross-subsidy | 26 | Use actual continuity and margins to tune tier uptake and service mix | Implementation Plan §§3,5; proposed M19–24 | Staff and consulting | 39
28 | Renew LGU / institutional agreements | 26 | Evidence-backed renewals and household payment fallbacks | Implementation Plan §§5,7; proposed M19–24 | Staff and consulting | 40
29 | Evaluate endline outcomes and affordability | 26,03 | Compare access, follow-through, costs and attended episodes with baseline | Implementation Plan §8; proposed M22–24 | Monitoring staff; new enumerator funding unitemized | 41
30 | Prepare continuation plan and final reporting | 26,27,28,29 (results) | Continuation operating plan, final financial report and research outputs | Implementation Plan §§5,8; proposed M23–24 | Staff, consulting and SPSS | 42
31 | GATE: approve continuation beyond Year 2 | 27,28,29,30 | Review renewals and >80% earned-revenue target; approve next period | Implementation Plan §5 target; M24 gate proposed | Milestone | 43
32 | Personnel, supervision and operating support | 01 | Continuous staffing, AI subscriptions, internet subscriptions and cloud operations | Budget: recurring personnel and MOOE in both years | PHP 2,974,560 / 2,734,560 personnel | 45
33 | Quality, safeguarding and caregiver re-screening | 08 | Routine case review, quarterly re-screening and clinical escalation | Implementation Plan §6; Service Catalog | Monitoring staff and consulting | 46
34 | Quarterly LGU billing and financial review | 02,17 (full report from M6) | Quarter-end billing; seasonality, collections, payouts and margin review | Implementation Plan §§3,5; Reporting Table 4 | Staff and monitoring | 47
35 | Commission PBX phones and support desk | 01,05 | PBX premium system and four extensions tested; contact routing agreed | Budget rows 52,59; proposed M2–M3 | Year 1 PBX equipment | 50
36 | Install servers, rack, network and storage | 01,05 | Rack, switch, two servers, SSDs and monitoring screens installed; role approved | Budget rows 53–57; proposed M2–M3 | Year 1 equipment; cloud hosting retained | 51
37 | Deploy generators and resilient site connectivity | 01,05 | Ten generators and Starlink units commissioned with site safety checks | Budget rows 43,45,58; proposed M2–M3 | Equipment, internet and utilities | 52
38 | Test backup power, failover and support procedures | 35,36,37 | Document power/network recovery tests, backup restoration and staff handover | Budget rows 52–59; proposed M3–M4 | Training and project laborers | 53
39 | Operate SMS, connectivity and infrastructure upkeep | 18 (SMS launch by M9),38 | SMS live at rollout; connectivity, power and equipment reviewed routinely | Budget rows 25,27,32,35; proposed M5–M24 | Bulk SMS PHP 12,000 per year; internet and utilities | 54
Infrastructure scope | On-premises equipment is budgeted, but its system role is not approved. Commissioning does not assume migration from the existing cloud platform.
Source register | Location
Rollout phases | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/Implementation Plan.md
Current project context | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/.brain/PROJECT_CONTEXT.md
Current work and dependencies | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/.brain/TODO.md
Current implementation | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/.brain/ARCHITECTURE.md
Approved decisions | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/.brain/DECISIONS.md
Service scope and training | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/Product/Service Catalog & Caregiver Operations.md
Reporting scope | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/Product/Reporting Engine & Dashboard Specifications.md
Automation roadmap | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/Architecture/Agentic AI & n8n Workflow Architecture.md
Research synthesis | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/Research/Comparative Benchmark Matrix.md
Revised budget | /Users/mclein/Downloads/AdvanCore-Expenses-2.xlsx

## Budget source
Revised expense workbook — source values and reconciliation
Source: AdvanCore-Expenses-2.xlsx, Sheet1!A1:G62. Original labels and figures preserved below.
| Year 1 |  | Year 1 | Year 2 | Year 2 |  | Reconciliation (PHP) | Year 1 | Year 2
I. | Personal Services | P |  | P |  | P | Personnel per source | 2974560 | 2734560
| Direct Cost | [5 empty] | MOOE per source | 13026199 | 3647000
| Salaries | [5 empty] | Grand total per source | 16000759 | 6381560
| Five (5) Porject Laborer 1 @ Php 21,816 x 12 mos |  | 1308960 |  | 1308960 |  | Personnel detail | 2974560 | 2734560
| Honoraria | [5 empty] | MOOE detail | 13064199 | 2867000
| One (1) Project Leader @ Php 8,800 x 12 mos |  | 105600 |  | 105600 |  | Grand total from detail | 16038759 | 5601560
| Six (6) Project Staff Level 3 @ Php 7,500 x 12 mos |  | 540000 |  | 540000 |  | Detail less source total | 38000 | -780000
| Six (6) Consulting Fee @ Php 10000 x 4 |  | 240000 |  | 240000 |  | Unexplained source balance | -38000 | 780000
Indirect Cost
(Implement Agency)
| Salaries | [5 empty] | Year 1 detail includes the PHP 38,000 PBX extension line. The source subtotal is lower by PHP 38,000. Year 2 source exceeds listed detail by PHP 780,000. No balancing expense invented.
| Sixteen (16) Enumerators and Digitizers (4 enums, 4 LGUs) @ Php 15000/mos |  | 240000
| Honoraria | [5 empty] | Quantities to confirm: “Two (3)” printers and “Twenty (25)” telehealth kits. SPSS says two years but carries PHP 10,000 in each year.
(Monitoring Agency)
Salaries
| Three (3) Project Staff Level 2 @ Php 15,000 x 12 mos |  | 540000 |  | 540000
Honoraria
| Sub-total for PS | P | 2974560 | P | 2734560 | P
II. | Maintenance and Other Operating Expenses
Direct Cost
Communication Expenses
| Transport Expenses |  | 200000 |  | 300000
| Internet Subscription Expenses |  | 48000 |  | 48000
Utility Expense
| Water, Electricity, and Cooking Fuel Expenses |  | 200000 |  | 300000
| Traning Expenses |  | 200000 |  | 300000
| Subscription Expenses |  | 390000 |  | 390000
| Website Domain (1 year) |  | 30000
| Ink, Bondapaper (12 mons) |  | 25000
| Cloud Hosting for Database (1 year, Stage 1: Production Scale) |  | 500000 | Stage 2: High Volume Scale | 1500000
| Apple Developer Fee |  | 7000 |  | 7000
| SPSS: Statistical Tool Software (2 years) |  | 10000 |  | 10000
| Bulk SMS (1 year) |  | 12000 |  | 12000
Indirect Cost
(Implementing Agency)
Supplies and Materials Expenses
| Two (2) MacBook M5 @ Php 110,000 |  | 220000
| Two (2) Lenovo V15 @Php 78,332 |  | 156664
| One (1)Epson WorkForce ES-50 Scanner @ Php 7,050 |  | 7050
| Two (3) Epson Ecotank L5290 Printer @ Php 13,495 |  | 40485
| Three (3) UPS for Wifi Router (10400mAh) @ Php 7,000 |  | 21000
| Twenty (25) Telehealth Suitcase @ Php 360,000 |  | 9000000
| Ten (10) Starlink @ Php 56,000 |  | 560000
| Four (4) Desktop @ Php 55,000 |  | 220000
| Four (4) Headset @ Php 5,000 |  | 20000
| Four (4) Monitor @ Php 6,000 |  | 24000
| Four (4) Keyboard @ 1,500 |  | 6000
| Four (4) Mouse @ Php 1,000 |  | 4000
| Four (4) Chair @ Php 6,500 |  | 26000
| One (1) IP Phone PBX Premium Package |  | 70000
| One (1) Equipment Rack (Orbita Digital RACK-27U-D) |  | 35000
| One (1) Failover Switch (24-port) |  | 125000
| Two (2) Server (Dell Poweredge R250)@ Php 125,000 |  | 250000
| Two (2) Storage (480GB Enterprise SATA SSD) @ Php 4,500 |  | 9000
| Two (2) Widescreen Monitor @ Php 80,000 |  | 160000
| Ten (10) Diesel Generator Set @ Php 45,000 |  | 450000
| Four (4) IP Phone PBX Extension @ Php 9,500 |  | 38000
| Sub-Total for MOOE | P | 13026199 |  | 3647000 | P
| GRAND TOTAL | P | 16000759 |  | 6381560 | P