## 24-month Gantt
advanCARE — Year 1 & Year 2 Gantt chart
Proposed 24-month implementation schedule. M1 = project start; calendar date pending.
Colored bars = activity window. ◆ = milestone. Amber section = proposed Months 19–24.
[5 empty] | YEAR 1 | [11 empty] | YEAR 2
ID | Activity / milestone | Start | End | Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
FOUNDATION & VALIDATION
01 | Mobilize project team and governance | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
02 | LGU / barangay MOUs and cost sharing | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
03 | Baseline survey and household digitization | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
04 | Privacy, clinical protocols and referral partners | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
05 | Procure equipment and connectivity | 1 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
06 | Complete pilot platform and verify real-use readiness | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07 | Recruit, screen and train first caregiver cohort | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08 | GATE: pilot readiness | 2 | 2 | 1 | bar: YEAR 1 2
CORE CARE PILOT
09 | Enroll households and assist first bookings | 2 | 4 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Deliver home care and post-discharge follow-up | 2 | 4 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Activate telehealth equipment in pilot sites | 3 | 4 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Review SLA, repeat use and caregiver continuity | 2 | 4 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | GATE: approve municipal expansion | 4 | 4 | 1 | bar: YEAR 1 4
MUNICIPAL EXPANSION
14 | Expand to 8–12 barangays in pilot municipality | 5 | 9 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Introduce pooled NEMT and referral coordination | 5 | 9 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Add respite packages, family updates and Rx routing | 5 | 9 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Complete tier registry and LGU reconciliation | 3 | 6 | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Add SMS, local languages and assisted access | 5 | 9 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | GATE: confirm municipal results | 9 | 9 | 1 | bar: YEAR 1 9
PROVINCIAL EXPANSION
20 | Stage expansion into additional municipalities | 10 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
21 | Formalize CVMC / institutional care contracts | 10 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
22 | Scale caregiver cohorts and train local trainers | 10 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
23 | Add elder knowledge-transfer wellness sessions | 10 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
24 | Introduce supervised workflow automation | 10 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
25 | Scale cloud hosting and performance monitoring | 13 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
26 | GATE: review provincial expansion | 18 | 18 | 1 | bar: YEAR 2 18
CONSOLIDATION & SUSTAINABILITY
27 | Optimize tier mix and rural cross-subsidy | 19 | 24 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
28 | Renew LGU / institutional agreements | 19 | 24 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
29 | Evaluate endline outcomes and affordability | 22 | 24 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
30 | Prepare continuation plan and final reporting | 23 | 24 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
31 | GATE: approve continuation beyond Year 2 | 24 | 24 | 1 | bar: YEAR 2 24
CONTINUOUS PROJECT SUPPORT
32 | Personnel, supervision and operating support | 1 | 24 | 24 | bar: YEAR 1 1 to YEAR 2 24
33 | Quality, safeguarding and caregiver re-screening | 2 | 24 | 23 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
34 | Quarterly LGU billing and financial review | 3 | 24 | 22 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Schedule details
Schedule basis and activity details
Schedule status | Proposed planning baseline, prepared 17 October 2026. Dates and owners are not yet approved.
Time basis | Year 1 = M1–M12; Year 2 = M13–M24. All activity windows include both start and end months.
Source timing | Phase 0 weeks 1–6 mapped to M1–M2. Phase 1 M2–M4; Phase 2 M5–M9; Phase 3 M10–M18 follow the vault.
Assumed timing | Task-level dates inside phases, procurement M1–M3, technical enhancements and all M19–M24 activities are proposed.
Existing implementation | App, API, staff console and care-loop prototype already exist as of 16 October. M1–M2 covers completion and validation for real use.
Source priority | Current .brain and implementation supersede older handoff snapshots. Research informs scope, not confirmed delivery dates.
Budget interpretation | Annual amounts support workstreams. No monthly cost allocation or grant disbursement schedule is inferred. Blank Year 2 costs remain blank.
Survey scope | Budget funds 16 enumerators/digitizers across four LGUs once in Year 1. Service rollout starts with one LGU; survey geography requires confirmation.
Equipment discrepancy | Budget row 26 says Twenty (25). PHP 9,000,000 / PHP 360,000 implies 25 kits; confirm quantity before procurement.
Funding gaps | No explicit new enumerator line in Year 2 or SMS gateway / Starlink recurring service line. Confirm provision before commitment.
Budget labels | Source row 45 says Sub-total for P S but contains CapEx + MOE. The source label is preserved.
Dependencies | IDs describe prerequisites or coordination links. Same-month work needs within-month sequencing. Gates require evidence before expansion.
Editing | Edit amber Start/End month cells on the Gantt (1–24). Duration, bars and milestone position update. Dependencies do not auto-reschedule.
Review cadence | Weekly pilot reviews and quarterly quality / finance reviews are continuous work windows, not separate monthly spending commitments.
ID | Activity | Dependencies | Expected output / gate | Source / timing basis | Budget alignment | Gantt row
01 | Mobilize project team and governance | — | Project leader, laborers, staff and monitoring roles assigned | Budget rows 5–16; Implementation Plan §3 | Personnel, both years | 9
02 | LGU / barangay MOUs and cost sharing | 01 | One municipality and 2–3 barangays; signed 50/50 funding mechanism | Implementation Plan §3 Phase 0; ADR-001 | Project staff and consulting | 10
03 | Baseline survey and household digitization | 01,02 (site access) | Baseline access, cost and care gaps; four-LGU survey scope to confirm | Implementation Plan §3 Phase 0; Budget row 13 | Enumerators / digitizers, Year 1 only | 11
04 | Privacy, clinical protocols and referral partners | 01 | Consent review, escalation protocol, RHU/CVMC coordination and hotline | TODO: non-code dependencies; Implementation Plan §3 | Consulting and staff | 12
05 | Procure equipment and connectivity | 01 | Computers, scanner/printers, telehealth kits and Starlink commissioned | Budget rows 21–33 | CapEx, Year 1 only | 13
06 | Complete pilot platform and verify real-use readiness | 01,04 | Validate existing care loop; separate demo data, secure storage and owned AI key | TODO P1–P4; ARCHITECTURE §§3–6; actual frontend/backend | Laborers, AI, hosting and mobile data | 14
07 | Recruit, screen and train first caregiver cohort | 01,04 | 15–20 screened caregivers, 40-hour training and skill badges | Implementation Plan Phase 0; Service Catalog §4 | Training, transport and food | 15
08 | GATE: pilot readiness | 02,03,04,06,07 | 30–50 households; 15–20 caregivers; signed cost sharing and ready care loop | Implementation Plan Phase 0 exit | Milestone | 16
09 | Enroll households and assist first bookings | 08 | BHW-led multilingual onboarding and published tier / service prices | Implementation Plan Phase 1 and §4 | Staff, transport and food | 18
10 | Deliver home care and post-discharge follow-up | 08 | Personal care, basic nursing support and respite; one formal follow-up | Implementation Plan Phase 1 | Staff and operating support | 19
11 | Activate telehealth equipment in pilot sites | 04,05,08 | Test clinician connectivity, operator training and escalation workflow | Budget telehealth / Starlink; Mobile App Specification | Year 1 equipment and training | 20
12 | Review SLA, repeat use and caregiver continuity | 08 | Weekly operations review with family feedback and corrective actions | Implementation Plan Phase 1 | Monitoring staff | 21
13 | GATE: approve municipal expansion | 09,10,11,12 | >60% SLA; >40% repeat use in 60 days; >70% caregiver retention | Implementation Plan Phase 1 exit | Milestone | 22
14 | Expand to 8–12 barangays in pilot municipality | 13 | Denser caregiver coverage and BHW enrollment network | Implementation Plan Phase 2 | Staff, training, transport and food | 24
15 | Introduce pooled NEMT and referral coordination | 13,04 | Shared transport routes and BHW / tele-nurse routing process | Implementation Plan Phase 2; Centene research | Transport and staff | 25
16 | Add respite packages, family updates and Rx routing | 13 | Long-distance family support and verified pharmacy / Yakap pathways | Implementation Plan Phase 2; Homage and Auxilio research | Staff, AI and hosting | 26
17 | Complete tier registry and LGU reconciliation | 02,06 | Server-side memberships; subsidy report and quarterly billing evidence | TODO P4; Reporting Specifications Table 4 | Laborers and staff | 27
18 | Add SMS, local languages and assisted access | 13,06 | Test low-bandwidth fallbacks and Tagalog / Ilocano / Ybanag support | TODO Later; Implementation Plan §§4,6 | Laborers and mobile data; SMS cost unitemized | 28
19 | GATE: confirm municipal results | 14,15,16,17,18 | 300–500 active members; lower transport cost; >70% discharge follow-through | Implementation Plan Phase 2 exit | Milestone | 29
20 | Stage expansion into additional municipalities | 19 | New LGU agreements and rollout waves as capacity and demand permit | Implementation Plan Phase 3 | Staff and Year 2 field expenses | 31
21 | Formalize CVMC / institutional care contracts | 19,04 | Badged hospital watchers and institutional revenue to support rural care | Implementation Plan Phase 3; Service Catalog §2 | Staff and consulting | 32
22 | Scale caregiver cohorts and train local trainers | 19,07 | Repeat screening, continuity incentives and trainer pipeline | Implementation Plan §§3,6; Honor research | Training, transport and food | 33
23 | Add elder knowledge-transfer wellness sessions | 19 | Intergenerational sessions integrated into wellness visits | Implementation Plan Phase 3 | Staff and field expenses | 34
24 | Introduce supervised workflow automation | 19,06 | Async matching notifications, care summaries and reporting with oversight | Agentic Architecture; ADR-006; TODO Later | Laborers, AI and hosting | 35
25 | Scale cloud hosting and performance monitoring | 20 (rollout demand) | Stage 2 capacity, backup/recovery checks and service monitoring | Budget row 39: Stage 2 Year 2; ARCHITECTURE | Year 2 hosting: PHP 1,500,000 | 36
26 | GATE: review provincial expansion | 20,21,22,23,24 | Review coverage, SLA, caregiver retention and unit economics before growth | Phase 3 ends M18; review gate proposed | Milestone | 37
27 | Optimize tier mix and rural cross-subsidy | 26 | Use actual continuity and margins to tune tier uptake and service mix | Implementation Plan §§3,5; proposed M19–24 | Staff and consulting | 39
28 | Renew LGU / institutional agreements | 26 | Evidence-backed renewals and household payment fallbacks | Implementation Plan §§5,7; proposed M19–24 | Staff and consulting | 40
29 | Evaluate endline outcomes and affordability | 26,03 | Compare access, follow-through, costs and attended episodes with baseline | Implementation Plan §8; proposed M22–24 | Monitoring staff; new enumerator funding unitemized | 41
30 | Prepare continuation plan and final reporting | 26,27,28,29 (results) | Continuation operating plan, final financial report and research outputs | Implementation Plan §§5,8; proposed M23–24 | Staff, consulting and SPSS | 42
31 | GATE: approve continuation beyond Year 2 | 27,28,29,30 | Review renewals and >80% earned-revenue target; approve next period | Implementation Plan §5 target; M24 gate proposed | Milestone | 43
32 | Personnel, supervision and operating support | 01 | Continuous staffing, AI subscriptions, mobile data and cloud operations | Budget: recurring personnel and MOE in both years | PHP 2,974,560 / 2,734,560 personnel | 45
33 | Quality, safeguarding and caregiver re-screening | 08 | Routine case review, quarterly re-screening and clinical escalation | Implementation Plan §6; Service Catalog | Monitoring staff and consulting | 46
34 | Quarterly LGU billing and financial review | 02,17 (full report from M6) | Quarter-end billing; seasonality, collections, payouts and margin review | Implementation Plan §§3,5; Reporting Table 4 | Staff and monitoring | 47
Source register | File / location
Implementation Plan | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/Implementation Plan.md
Operational context | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/.brain/PROJECT_CONTEXT.md
Current status and dependencies | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/.brain/TODO.md
Architecture and implementation | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/.brain/ARCHITECTURE.md
Approved decisions | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/.brain/DECISIONS.md
Service and training scope | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/Product/Service Catalog & Caregiver Operations.md
Reporting requirements | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/Product/Reporting Engine & Dashboard Specifications.md
Automation roadmap | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/Architecture/Agentic AI & n8n Workflow Architecture.md
Research synthesis | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/Research/Comparative Benchmark Matrix.md
Vault index | /Users/mclein/Documents/Developer/Personal_Projects/AdvanCare/AdvanCare/AdvanCare Master MOC.md
Budget | /Users/mclein/Downloads/AdvanCore-Expenses.xlsx

## Budget source
Expense workbook — source values
Source: /Users/mclein/Downloads/AdvanCore-Expenses.xlsx, Sheet1, A1:D47. Values and labels preserved below.
Year 1 | Year 1 | Year 2 | Year 2 | Budget reconciliation (PHP) | Year 1 | Year 2
Personal Services |  |  |  | Personnel | 2974560 | 2734560
Direct Cost |  |  |  | CapEx + MOE | 11901664 | 2845000
Salaries |  |  |  | Total per source | 14876224 | 5579560
Five (5) Porject Laborer 1 @ Php 21,816 x 12 mos | 1308960 |  | 1308960 | Total of detail lines | 14876224 | 5579560
Honoraria |  |  |  | Difference | 0 | 0
One (1) Project Leader @ Php 8,800 x 12 mos | 105600 |  | 105600
Six (6) Project Staff Level 3 @ Php 7,500 x 12 mos | 540000 |  | 540000
Six (6) Consulting Fee @ Php 10000 x 4 | 240000 |  | 240000 | No monthly cost allocation assumed.
Indirect Cost
(Implement Agency)
Salaries
Sixteen (16) Enumerators and Digitizers (4 enums, 4 LGUs) @ Php 15000/mos | 240000
Honoraria
(Monitoring Agency)
Salaries Three (3) Project Staff Level 2 @ Php 15,000 x 12 mos | 540000 |  | 540000
Honoraria
Sub-total for P S | 2974560 |  | 2734560
CapEx
two (2) MacBook M5 @ Php 110,000 | 220000
Two (2) Lenovo V15 @Php 78,332 | 156664
One (1)Epson WorkForce ES-50 Scanner @ Php 7,050 | 7050
Two (2) Epson Ecotank L5290 Printer @ Php 13,495 | 26950
Three (3) UPS for Wifi Router (10400mAh) @ Php 7,000 | 21000
Twenty (25) Telehealth Suitcase @ Php 360,000 | 9000000
Ten (10) Starlink @ Php 56,000 | 560000
Four (4) Desktop @ Php 55,000 | 220000
Four (4) Headset @ Php 5,000 | 20000
Four (4) Monitor @ Php 6,000 | 24000
Four (4) Keyboard @ 1,500 | 6000
Four (4) Mouse @ Php 1,000 | 4000
Four (4) Chair @ Php 6,500 | 26000
MOE
Five (5) AI Subscription @ Php 6,500 x 12 mos | 390000 |  | 390000
Four (4) Mobile Data @ Php 1000 x 12 mos | 48000 |  | 48000
Website Domain (1 year) | 30000
Ink, Bondapaper (12 mons) | 25000
Cloud Hosting for Database (1 year, Stage 1: Production Scale) | 500000 | Stage 2: High Volume Scale | 1500000
Apple Developer Fee | 7000 |  | 7000
SPSS: Statistical Tool Software (2 years) | 10000
Traning Expenses | 200000 |  | 300000
Transport Expenses | 200000 |  | 300000
Food | 200000 |  | 300000
Sub-total for P S | 11901664 |  | 2845000
Total | 14876224 |  | 5579560